## Main Dashboard
!!! DISCLAIMER !!! |  |  |  |  | • "HLRM rec." refers to the "High-Level Roadmap" recommendations published by the EU T+1 Industry Committee in June 2025 • "RTS provision" refers to the provisions set out in ESMA's "Final Report On Amendments to the RTS on Settlement Discipline" (October 2025) • "Testing Plan rec." refers to the "Testing Plan" recommendations published by the EU T+1 Industry Committee in March 2026 • "AMI-SeCo CEG standards" refers to the standards set out in the "T+1 Corporate Events Harmonised Implementation Guide" published by the AMI-SeCo CEG in March 2026 --> All documents are available on the EU T+1 Industry Committee website under “Guides & Resources”: https://eu-t1.eu/resources-2/ and on ESMA portal: https://www.esma.europa.eu/document/
In case of discrepancies between this table and the latest official communication of the relevant CSD, the latter prevails. ECSDA accepts no liability for the content of this Dashboard, which is provided for the purposes of a high-level overview across European markets and ensuring transparency in advancement of the preparation, allowing CSD participants and other FMIs to prepare the move in an orderly way.
Current dashboard release: June 2026 |  |  |  |  | TESTING | [10 empty] | SETTLEMENT | [36 empty] | CORPORATE EVENTS**
A snapshot will be taken every three/four months and will be made publicly available on the ECSDA website. |  |  |  |  | Industy testing windows | [9 empty] | Additional info | Securities Settlement System Timings | [11 empty] | Tools and Functionalities | [19 empty] | SFT |  |  |  | Additional info | Key Dates |  |  | Buyer Protection |  |  | Market Claims |  |  | Transformation |  |  | Additional info
[5 empty] | Window 1 |  | Window 2 |  | Window 3 |  | Window 4 |  | Window 5 |  | Any other relevant information for participants | ST-02.1 – Securities Settlement System Timings (SSS Opening) |  |  |  | ST-02.2 – Securities Settlement System Timings (SSS Closing EUR) |  |  |  | ST-02.3 – Securities Settlement System Timings (SSS Closing non-EUR) |  |  |  | ST-03.1 – Partial settlement functionality |  |  |  | ST-03.5 – Hold & Release functionality |  |  |  | ST-03.8a – Allegements |  |  |  | ST-03.9 – PoA Functionality |  |  |  | ST-03.14 – Auto-collateralisation facilities |  |  |  | SF-01 – Further analysis of potential settlement optimisation for SFTs |  |  |  | Any other relevant information for participants | CE-01 – Alignment of corporate event key dates with the T+1 standard settlement cycle |  |  | CE-02 – Automation of buyer protection processing |  |  | CE-03 – Automation of market claims processing |  |  | Transformation process |  |  | Any other relevant information for participants
[5 empty] | All FMIs available for testing. Blue period (= testing automation and existing/new functionalities) |  | All FMIs available for testing. Green period (= testing Blue period + new operational timetable) | [8 empty] | Securities settlement systems should open for settlement at the latest by 00:00 on SD. Settlement instructions received by securities settlement systems after this time will still be submitted for settlement in subsequent cycle. |  |  |  | If not already the case, establish a DvP cutoff of 16:00 for standard settlement in EUR and a FoP cutoff of 18:00. It is noted that some outliers in EUR settlement may occur (e.g. ICSD settlement) |  |  |  | Align the DvP cut off of non-EUR European currencies to 16:00 to promote consistency and efficiency of funding and inventory management processes |  |  |  | Provide partial settlement functionality (including partial release), without any exception |  |  |  | Provide full Hold & Release functionality (including partial release), without any exception |  |  |  | Support the identification and reporting of allegements, without any exception |  |  |  | Provide PoA functionality, including instruction of ‘already matched’ where applicable. This includes T2S already matched PoA services being offered by CSDs to both DCP & ICPs |  |  |  | Make auto-collateralisation facilities available to all market participants to support intraday liquidity provision. This recommendation applies to T2S auto-collateralisation, as well as equivalent tools provided by non-T2S CSDs |  |  |  | Every CSDs (even in T2S) will need to confirm whether they will implement the SFT gating event |  |  |  |  | CSDs to support automatic realignment of CA key dates to T+1 (ex‑date/record‑date same day; reorganisations intervals updated); apply transition rules around go‑live |  |  | Automate end‑to‑end buyer‑protection processing (detect CA, notify chain, capture buyer‑protection/election within shortened windows) |  |  | Implement harmonised ISO messages for claim creation/status/amendments; reduce manual handling in shortened timelines |  |  | Automate transformation of pending transactions (cancel and replace with CA outturn instructions)
| CSD Key Operational Information |  |  |  | Testing Plan rec. | [10 empty] | HLRM rec. |  |  |  | HLRM rec. |  |  |  | HLRM rec. |  |  |  | HLRM rec. & RTS provision |  |  |  | HLRM rec. & RTS provision |  |  |  | HLRM rec. (Market Practice forthcoming) |  |  |  | HLRM rec. |  |  |  | HLRM rec. & RTS provision |  |  |  | HLRM rec. (Market Practice forthcoming) |  |  |  |  | HLRM rec. & AMI-SeCo CEG standards |  |  | HLRM rec. & AMI-SeCo CEG standards |  |  | HLRM rec. & AMI-SeCo CEG standards |  |  | AMI-SeCo CEG standards |  |  |  | CSD Publication of T+1 Operational Documentation
[5 empty] | 01-12 Feb 2027 |  | 19-30 Apr 2027 |  | 17-28 May 2027 |  | 28 Jun-09 Jul 2027 |  | 23 Aug-10 Sep 2027* |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct-27 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  | By 11 Oct 2027 |  |  |  |  | By 11 Oct 2027 |  |  | By 11 Oct 2027 |  |  | By 11 Oct 2027 |  |  | By 11 Oct 2027 |  |  |  | Availability of operational documentation supporting T+1 readiness (eg. Rules of Operation, Terms&Conditions, Testing Guidelines, or any other functional updates).
| SSS Jurisdiction | CSD Name | Public contact email | T2S Connectivity | Open? | Comments (if any) | Open? | Comments (if any) | Open? | Comments (if any) | Open? | Comments (if any) | Open? | Comments (if any) | Free text | Will you align by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you align by Oct-27? | If Y, by when? | If N, what cut-off will you apply? | Comments (if any) | Will you align by Oct-27? | If Y, by when? | If N, what cut-off will you apply? | Comments (if any) | Will you adhere by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you adhere by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you adhere by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you adhere by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you adhere by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you propose by Oct-27? | If Y, by when? | If N, will the flag be ignored, or will the instruction be rejected? | Comments (if any) | Free text | Will you implement by Oct-27? | If P, please list the non-applied standards (eg. KD1, KD2, …, KD7) | Comments (if any) | Will you implement by Oct-27? | If P, please list the non-applied standards (eg. BP1, BP2, ..., BP19) | Comments (if any) | Will you implement by Oct-27? | If P, please list the non-applied standards (eg. MC1, MC2, …, MC23) | Comments (if any) | Will you implement by Oct-27? | If P, please list the non-applied standards (eg. TF1, TF2, …,TF16) | Comments (if any) | Free text | Published? | URL | If N, estimated publication date? | Comments (if any)
| EEA COUNTRIES |  |  |  | EEA COUNTRIES | [10 empty] | EEA COUNTRIES | [36 empty] | EEA COUNTRIES | [12 empty] | EEA COUNTRIES
| AT | OeKB |  | In T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  | Individual already matched solutions have to be discussed with our settlement team. | Yes | Already available |  |  | Yes | By 2nd testing window |  |  |  | Full |  |  | None |  |  | Partial |  |  | Unknown |  |  |  | No |  | Q1 2027.
| BE | Euroclear Bank | Tplus1@euroclear.com | In T2S (not yet live) | [61 empty] | Yes | https://my.euroclear.com/eb/en/reference/t-1-for-euroclear-bank-clients.html | Please refer to our implementation guide " The road to T+1 settlement in Europe,Your guide to navigate the change" for further information. End 2026 a detailed testing guide will be published as well. | Our guide is updated every quarter with the latest news and information.
|  |  |  | Outside T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | Euroclear Bank testing environment is available on demand and is operated in a real--time mode. Euroclear Bank will provide its testing and implementation plan by end of Q2 2026. | Yes | By Oct-27 |  | Target implementation September 2027. While Euroclear Bank will continue to operate an extended operational day to meet global clients needs, we intend to implement various changes to our operational day. Indeed, to prepare for the transition to T+1 settlement, we aim to implement one important change to our operating model. We intend to remove settlement from our current overnight batch process and open real-time settlement earlier at around 23:00 CET. | No |  | Euroclear Bank already has a settlement deadline for internal settlement at 16:00 for EUR but we will continue to operate an extended operational day with a free of payment (FOP) cut-off at 19:30 to serve global clients. |  | Yes | By 2nd testing window |  | Target implementation March 2027 for the new internal DVP cut offs and September 2027 for Bridge cut offs. Euroclear Bank will extend the DVP mandatory settlement windows for non-EUR European currencies to align with the EUR cut-off for its internal and Bridge settlement. | Yes | Already available |  | Euroclear Bank already offers both auto-partial settlement and partial release today. | Yes | Already available |  | Euroclear Bank already offers hold and release today. | Yes | Already available |  | Euroclear Bank already offers allegements reporting today via multiple communication channels. | Yes | Already available |  | Euroclear Bank already offers POA services today. | Yes | Already available |  | Euroclear Bank offers clients an equivalent collateral facility to support credit lines. | Yes | Target implementation date: June 2027. |  | Euroclear Bank will implement the new gating event. |  | Partial | Most of Key Dates are set by Issuers and their agents. Deviation from recommendations can happen. |  | Partial | Only BP1-BP4 will be implemented. |  | Partial | Gap on Bridge transacation where EB detects but don't process the MC. MC2-5, MC 11-13 are implemented. Other ones requires adaptations and analysis is ongoing. |  | Partial | Gap on Bridge transacation where EB detects but don't process the Transformation. Gap on TF6 and TF12 under analysis.
| BE/FR/NL | Euroclear Belgium/France/Netherlands | Tplus1@euroclear.com | In T2S | Yes |  | Yes | ESES CSDs will activate the live-timing testing platform during the dedicated windows. | Yes | ESES CSDs will activate the live-timing testing platform during the dedicated windows. | Yes | ESES CSDs will activate the live-timing testing platform during the dedicated windows. | Yes | ESES CSDs will activate the live-timing testing platform during the dedicated windows. | ESES testing environment is available on demand. ESES CSDs will activate the live-timing testing platform during the dedicated windows. | Yes |  |  | ESES CSDs as T2S CSDs will adapt their operational day following the implementation of the T2S change request CR0858 in June 2027. | Yes | Already aligned |  | The ESES CSDs settle transactions in EUR and already have a DvP cut-off at 16:00 (CET) today and a FoP cutoff at 18:00. |  |  |  | N/A as settlement occurs in EUR only. | Yes | Already available |  | The ESES CSDs already offer clients an auto-partial settlement and Client Partial Release service. | Yes | Already available |  | The ESES CSDs already offer hold and release today. | Yes | Already available |  | The ESES CSDs already offer allegements reporting today. | Yes | Already available |  | The ESES CSDs already offer POA services today. | Yes | Already available |  | The ESES CSDs already offer access to auto-collateral services. | Yes | 2027-06-01 |  | The ESES CSDS will offer access to the new gating event via T2S for our Directly Connected Party (DCP) clients and via ISO15022 and EuroclearConnect for Screens for our Indirectly Connect Party (ICP) clients. |  | Full | Most of Key Dates are set by Issuers and their agents. Deviation from recommendations can happen (like marginally today). |  | Partial | Only BP1-BP4 will be implemented. |  | Partial | Analysis ongoing for MC8, MC9, MC14, MC15 where the implementation is not guaranteed yet. |  | Partial | Analysis ongoing for TF6 and TF12where the implementation is not guaranteed yet. |  |  | Yes | https://my.euroclear.com/eses/shared/en/reference/t-1-for-eses-clients.html | Please refer to our implementation guide " The road to T+1 settlement in Europe,Your guide to navigate the change" for further information. End 2026 a detailed testing guide will be published as well. | Our guide is updated every quarter with the latest news and information.
| FI | Euroclear Finland | t2s.finland@euroclear.com | In T2S | Yes | Exact testing schedule to be confirmed. | Yes | Exact testing schedule to be confirmed. | Yes | Exact testing schedule to be confirmed. | Yes | Exact testing schedule to be confirmed. | Yes | Exact testing schedule to be confirmed. |  | Yes |  |  |  | Yes | Already aligned |  |  | Unknown |  |  | N/A as settlement occurs in EUR only. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | By 2nd testing window |  |  |  | Full |  |  | None | No automated BP by Oct 2027. |  | Partial | MC1, MC11 partially, MC17 not implemented, no harmonised MC messages. |  | Partial | TF1, TF6, TF9 partially implemented. |  |  | No |  | By end of June 2026.
| SE | Euroclear Sweden |  | Outside T2S | Yes | Exact testing schedule to be confirmed in collaboration with the market. | Yes | Exact testing schedule to be confirmed in collaboration with the market. | Yes | Exact testing schedule to be confirmed in collaboration with the market. | Yes | Exact testing schedule to be confirmed in collaboration with the market. | Yes | Exact testing schedule to be confirmed in collaboration with the market. | Euroclear Sweden testing environment does not support cross-border testing. | No |  | When joining T2S in 2030. |  | Yes | Before 1st testing window | Will be moved effective 12 October 2026. | FoP cutoff will remain at 17:00 until joining T2S 2030. | Yes | Before 1st testing window |  | Will be moved effective 12 October 2026. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  | Unlike T2S, our solution does not support already matched instructions; therefore, the instructing AO must submit both its own instruction and the instruction for the AO for which it has been granted POA. | Yes | Already available |  |  | No |  | Ignore |  |  | Partial |  |  | None | ESw will take this into consideration once a platform migration has been completed. |  | None | ESw will take this into consideration once a platform migration has been completed. | ESw support manual re-bookings of payments. | None | ESw will take this into consideration once a platform migration has been completed. |  |  | Yes | https://my.euroclear.com/dam/ESw/Private_client_info/Guides | Please refer to our implementation guide " The road to T+1 settlement in Europe.
| BG | CD AD |  | In T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | CDAD plans participation in both Blue and Green testing periods, including functional, interoperability and operational timetable testing related to T+1 settlement and corporate actions processing. | Yes |  |  |  | Yes | By Oct-27 |  | 12 Oct.2026. | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already available |  |  | Unknown |  |  |  | Unknown |  |  |  |  | Full |  |  | Full |  |  | Full |  |  | Full |  |  |  | No |  | Q1-Q2/27.
| ES | Iberclear | proyectot1@grupobme.es | In T2S | Yes |  | Yes | Live Timing. | Yes | Live Timing. | Yes | Live Timing. | Yes | Live Timing. | Iberclear testing environment is always available. | Yes |  |  |  | Yes | Already aligned |  |  | Unknown |  |  | Not applicable. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | By 2nd testing window |  |  |  | Full |  |  | Partial | Only BP3, BP4 and BP19 are currently implemented. |  | Full |  |  | Full |  |  | Iberclear will offer settlement messages (MT54X) and custody messages (MT567, MT599, MT566,Seev.050-53) for market claims. | Yes
| CY | CSE | info@cse.com.cy | Outside T2S | Yes | Τhe test environment will be in T+2 settlement cycle, due to technical reasons regarding the migration of the Athens Exchange trading (the CSE is using the same trading system) to the Optiq platform of Euronext in June 2027 | Yes | Τhe test environment will be in T+2 settlement cycle, due to technical reasons regarding the migration of the Athens Exchange trading (the CSE is using the same trading system) to the Optiq platform of Euronext in June 2027 | Yes | Τhe test environment will be in T+2 settlement cycle, due to technical reasons regarding the migration of the Athens Exchange trading (the CSE is using the same trading system) to the Optiq platform of Euronext in June 2027 | Yes | The test environment will be in T+1 settlement cycle | Yes | The test environment will be in T+1 settlement cycle |  | Unknown |  |  | The matter is still under investigation. | [8 empty] | Yes | By 1st testing window |  |  | Yes | By 1st testing window | [10 empty] | Unknown |  |  | The CSE is not a T2S CSD and therefore this adjustment is currently marked as frozen. | No |  | Unknown | Further analysis is needed. | [14 empty] | No | Available to all Members and Participants. | Q1 2027.
| CZ | CDCP CZ | rozvoj@pse.cz | Outside T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | No |  | Given the settlement model applied by the Central Securities Depository, under which T2S night-time processing functionalities are available within the Central Securities Depository during the day, and also considering the absence of RTGS settlement, CSD Prague proposes to maintain the current start of settlement at 7:00 and the opening of the settlement system for participants at 8:00. |  | Yes | Before 1st testing window |  | FoP cutoff will be implemented by 11 Oct 2027. | Unknown |  |  | Depends on decision of Czech National Bank. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Unknown |  |  |  | Unknown
| DE | Clearstream Europe | T+1@clearstream.com | In T2S | Yes | Only existing functionalities. | Yes |  | Yes |  | Yes |  | Yes |  | Testing is available on demand and a detailed test planning will be published Q4 2026. | Yes |  |  |  | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | By 2nd testing window |  |  |  | Partial | See Comment. | Key dates are largely set by Issuers/Agents. Clearstream will raise awareness and encourage usage of standard key date sequences, but deviations cannot be excluded at this time. Hence we mark this point as partial. | Partial | All except BP3, BP4 and BP19. |  | Partial | MC7, MC19. |  | Partial | TF3. |  |  | Yes | https://www.clearstream.com/clearstream-en/securities-services/custody-and-investor-solutions/journey-to-t1
| LU | Clearstream Banking | T+1@clearstream.com | Outside T2S | Yes | Only existing functionalities. | Yes |  | Yes |  | Yes |  | Yes |  | Testing is available on demand and a detailed test planning will be published Q4 2026. | No |  |  | Not a T2S CSD, Settlement System timings are set to accommodate global clients. | No |  | As an ICSD the cut offs accommodate international clients as well. However , no impact expected as our internal EUR cut-offs are already in line with the recommendations. | Outside T2S. | No |  | As an ICSD the cut offs accommodate international clients as well. However, no impact expected as our internal EUR cut-offs are already in line with the recommendations. | Outside T2S. | Yes | Already available |  | Cross CSD domestic partial settlement currently under investigation. | Yes | Already available |  |  | Yes | Already available |  | Clearstream is investigating domestic market allegements. | Yes | Already available |  |  | Yes | Already available |  | Auto-collateralisation by means of credit line usage. | Yes | Unknown |  |  |  | Partial | See Comment. | Key dates are largely set by Issuers/Agents. Clearstream will raise awareness and encourage usage of standard key date sequences, but deviations cannot be excluded at this time. Hence we mark this point as partial. | Partial | All except BP3, BP4 and BP19. |  | Partial | MC19 + see comment. | Analysis ongoing re Market Claims for transactions across the Bridge. | Partial | See comment. | Analysis ongoing re Transformatoins for transactions across the Bridge. |  | Yes | https://www.clearstream.com/clearstream-en/securities-services/custody-and-investor-solutions/journey-to-t1
| LU | LuxCSD | T+1@clearstream.com | In T2S | Yes | Only existing functionalities. | Yes |  | Yes |  | Yes |  | Yes |  | Testing is available on demand and a detailed test planning will be published Q4 2026. | Yes |  |  |  | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | By 2nd testing window |  |  |  | Partial | See Comment. | Key dates are largely set by Issuers/Agents. Clearstream will raise awareness and encourage usage of standard key date sequences, but deviations cannot be excluded at this time. Hence we mark this point as partial. | Partial | All except BP3, BP4 and BP19. |  | Full | MC19. |  | Full |  |  |  | Yes | https://www.luxcsd.com/luxcsd-en/products-and-services/settlement/overview
| DK | Euronext Securities ¦ Copenhagen | CPH-clientsupport@euronext.com | In T2S | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. | High level test strategy and readiness plan will be shared on 30/06/26. | Yes |  |  | At the current stage, the release in production of this intervention is planned for June 27. | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Unknown |  |  |  | Full |  |  | None |  |  | Full |  |  | Full |  |  |  | No | T+1 programme ¦ Euronext | A first version of the client specifications will be shared at end of Q2 26 An High-Level Overview on the Testing Strategy will be shared at the end of Q2 26.
|  |  |  | Outside T2S (DKK) | Unknown | Ongoing checks to define the availability in this Window. | Unknown | Ongoing checks to define the availability in this Window. | Unknown | Ongoing checks to define the availability in this Window. | Unknown | Ongoing checks to define the availability in this Window. | Unknown | Ongoing checks to define the availability in this Window. | [5 empty] | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Unknown |  |  |  | Full |  |  | None |  |  | Full |  |  | Full
| IT | Euronext Securities ¦ Milan | eam@euronext.com | In T2S | Yes | Yes - Business as usual (BAU) standard testing conditions, no live-timing; participants are encouraged to test existing connectivity and processes. | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs |  | Yes |  |  | At the current stage, the release in production of this intervention is planned for June 27. | Yes | Already aligned | [10 empty] | Yes | Unknown |  |  | Yes | Already available |  |  | Yes | Unknown |  |  | Yes | Already available |  |  | Yes | Unknown |  |  |  | Full |  |  | None |  |  | Full |  |  | Full |  |  |  | No | https://www.euronext.com/en/regulation/t1-programme | A first version of the client specifications will be shared at end of Q2 26 An High-Level Overview on the Testing Strategy will be shared at the end of Q2 26.
| NO | Euronext Securities ¦ Oslo | OSL-clientsupport@euronext.com | Outside T2S | Unknown | Ongoing checks to define the availability in this Window. | Unknown | Ongoing checks to define the availability in this Window. | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. | Yes | Exact testing schedule and conditions pending further analysis. |  | Yes |  |  | Norwegian market follows the opening hours of the Norwegian Central Bank (non-EUR central bank). | Yes |  | •DvP cutoff of 16:00 CET for standard settlement in EUR is not relevant for ES-OSL as settlement is in NOK only. •Will implement a FoP batch settlement at 18:00 CET. |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  | Unknown |  |  | Partial | KD2, KD4, KD7. |  | None |  |  | None |  |  | None |  |  |  | No | https://www.euronext.com/en/regulation/t1-programme | A first version of the client specifications will be shared at end of Q2 26 An High-Level Overview on the Testing Strategy will be shared at the end of Q2 26.
| PT | Euronext Securities ¦ Porto | clientservices-es-pto@euronext.com | In T2S | Yes | Yes - Business as usual (BAU) standard testing conditions, no live-timing; participants are encouraged to test existing connectivity and processes. | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs | Yes | Yes - E2E testing available in T+1 conditions on dedicated ISINs |  | Yes |  |  | At the current stage, the release in production of this intervention is planned for June 27. | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Unknown |  |  |  | Full |  |  | None |  |  | Full |  |  | Full |  |  |  | No | https://www.euronext.com/en/regulation/t1-programme | A first version of the client specifications will be shared at end of Q2 26 An High-Level Overview on the Testing Strategy will be shared at the end of Q2 26.
| GR | Euronext Securities ¦ Athens | athens-members-support@euronext.com | Outside T2S | Yes | The test environment will be in T+2 settlement cycle, due to technical reasons ahead of the migration of the Athens Exchange trading to the Optiq platform of Euronext in June 2027. | Yes | The test environment will be in T+2 settlement cycle, due to technical reasons ahead of the migration of the Athens Exchange trading to the Optiq platform of Euronext in June 2027. | Yes | The test environment will be in T+2 settlement cycle, due to technical reasons ahead of the migration of the Athens Exchange trading to the Optiq platform of Euronext in June 2027. | Yes | The test environment will be in T+1 settlement cycle. | Yes | The test environment will be in T+1 settlement cycle. |  | Unknown |  |  | The matter is still under investigation. Currently, the 1st settlement cycle runs at 02:00 for DvD and at 09:00 continues for the multilateral settlement and at 09:30 for DvP. Following consultation with Members and Participants, an extension of the operating hours of the Euronext Securities Athens Securities Settlement System will be decided. | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By 1st testing window |  |  | Yes | Before 1st testing window |  |  | Yes | Already available |  |  | Yes | By 5th testing window |  |  | Unknown |  |  | Given that Euronext Securities Athens (ES-ATH) is not a T2S CSD, the fact that during the night settlement the DvD (Delivery vs Delivery) cycles of ES-ATH BIS 2 model take account of that feature and thus reduce significantly the required settlements, this adjustment is currently marked as “Frozen (TBC)”. Further updates will be provided once relevant issues have been assessed. | No |  | Unknown | Further analysis of potential settlement optimisation for SFTs: Further update will be provided once relevant issue has been assessed. |  | Partial | KD5, KD6, KD7. |  | None |  |  | Partial | MC7, MC18, MC19, MC20, MC21,MC22, MC23. |  | Full |  |  |  | Yes | Private area (Accredited Users Area) of Euronext Athens' website, accessible to Members and Participants. https://portal.athexgroup.gr/web/guest/ |  | The T+1 operational documentation and additional material (technical manuals, testing guidelines, and testing scenarios) is published in the Accredited Users Area of Euronext Athens' website, accessible to Members and Participants.
| HR | SKDD |  | In T2S | Yes | SKDD’s testing environment will be fully accessible and opened to market participants upon request, enabling them to validate their major internal system developments starting from Window 1 (February 2027). SKDD’s specific functional updates—consisting of minor system adjustments for automated market claims, transformations , automatic partial settlement, and daily operational timetable changes —are scheduled for deployment and active testing during Q2 or Q3 2027. | Yes |  | Yes |  | Yes |  | Yes |  |  | Yes |  |  |  | Yes | Already aligned |  |  | Yes |  |  |  | Yes | By 3rd testing window |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Unknown |  |  |  |  | Full |  |  | None |  |  | Full |  |  | Full |  |  |  | No |  | Q4 2026.
| HU | KELER | tfo@keler.hu | In T2S | No |  | No |  | No |  | No |  | No |  | KELER's one of a kind transactional set-up in T2S does not require client testing. | No |  |  | KELER's one of a kind transactional set-up in T2S does not require this timing. | No |  |  | KELER's one of a kind transactional set-up in T2S does not require this timing. | No |  |  | KELER settles in T2S EUR only. | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  | Ignore |  | KELER's one of a kind transactional set-up in T2S does not utilise these functions. | Full |  |  | Unknown |  |  | Unknown |  |  | Unknown |  |  |  | No |  | 2026-06-30
|  |  |  | Outside T2S (HUF) | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Implementation plan will tell more about testing periods. | No |  |  | Hungarian market's and KELER's own operational set-up does not allow night time settlement. | Yes | By Oct-27 |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Unknown |  |  |  | No |  | Ignore |  |  | Full |  |  | Unknown |  |  | Unknown |  |  | Unknown
| IS | VBM |  | Outside T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | No |  |  | SSS opens at 8:00 am. |  |  |  |  | Yes | Already aligned |  |  | Unknown |  |  |  | Yes |  |  | Hold and release available, partial release TBD. | Yes | Already available | [6 empty] | No |  |  |  | Unknown |  |  |  |  | Full |  |  | None |  |  | Unknown |  |  | Unknown |  |  |  | No
| IS | Nasdaq CSD | csd.ops@nasdaq.com | Outside T2S | Yes | Internal testing only. | Yes |  | Yes |  | Yes |  | Yes |  | Detailed test planning to be confirmed. | No |  |  |  | Yes | Already aligned |  |  | Yes | Already aligned |  |  | Yes | Already available |  |  | Yes | Already available |  | Hold and release available, partial release TBD. | Yes | Already available |  |  | Yes | By Oct-27 |  |  | No |  |  |  | Unknown |  |  |  | Will not be supported in Iceland. | Full |  | Key dates are set by issuers so deviations from recommendations can happen. | None |  |  | Full |  |  | Full |  |  |  | No |  | Q4 2026.
| LV/EE/LT |  |  | In T2S | Yes | Internal testing only. | Yes |  | Yes |  | Yes |  | Yes |  | Detailed test planning to be confirmed. | Yes |  |  |  | Yes | Already aligned |  |  | Unknown |  |  | No settlement in other non-EUR European currencies. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | By Oct-27 |  |  | Yes |  |  |  | Unknown |  |  |  | TBD in Baltic markets. | Full |  | Key dates are set by issuers so deviations from recommendations can happen. | None |  |  | Full |  |  | Full |  |  |  | No |  | Q4 2026.
| MT | MSE |  | In T2S | Yes |  |  | To be confirmed. |  | To be confirmed. |  | To be confirmed. |  | To be confirmed. | Deadlines with regards to Allocations, Confirmations and Matching are already in line with T+1 deadlines for domestic market. We will coordinate with other CSDs where applicable. | Yes |  |  | SSS schedule will remain concurrent to the T2S schedule. | Yes | Already aligned |  | DVP Cutoff is aligned to 16:00 and FOP is aligned to 18:00. | Yes | Already aligned |  |  | No |  |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | To be discussed. | Partial |  |  | Partial | Analysis ongoing. |  | Partial | Analysis ongoing. |  | Partial | Analysis ongoing. |  |  | No |  | Q1 2027.
| PL | KDPW |  | Outside T2S | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Unknown |  |  | No |  | There is no market demand for night time settlement. |  | Yes | Already aligned |  | For EUR DvP cut off is 16:00; for FoP cut off is 18:30. | Yes |  |  | For PLN DvP cut off is 17:00. | Yes | Already available |  |  | Yes |  |  | Hold and release available; partial release TBC. | Yes | By Oct-27 |  |  | Yes | Already available |  |  | Unknown |  |  |  | No |  | Ignore |  |  | Full |  |  | None |  |  | None |  |  | None |  |  |  | Yes | https://www.kdpw.pl/en/implementation-of-the-t1-settlement-cycle.html
| RO | Depozitarul Central | projects_csdr@roclear.ro | In T2S | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Depozitarul Central’s test environment is continuously available for testing both on the local platform and in T2S. Thus, mechanisms that have already been implemented, such as hold/release and allegements, can be tested at any time, while partial settlement and partial release will be available no later than Q2 2027. | Yes |  |  |  | Yes |  |  | Already aligned. |  |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes |  |  |  | Yes | Already available |  |  | No |  |  |  | No |  | Ignore |  |  | Full |  |  | Partial | BP5, BP6, BP7, BP8, BP9, BP10, BP11, BP12, BP13, BP14, BP15, BP16, BP17, BP18. |  | Full |  |  | Full |  |  |  | No |  | Q1 2027.
|  |  |  | Outside T2S (RON) | Unknown |  | Unknown |  | Unknown |  | Unknown |  | Unknown |  |  | No |  |  | The settlement process will begin at 7:30 CET. The NCB’s local currency cash settlement system does not operate overnight. Depozitarul Central will extend its local platform availability for overnight instruction receipt, matching and status reporting, latest on Oct 2027. |  |  |  |  | Yes |  |  | Already aligned. | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes |  |  |  | Yes | Already available |  |  | No |  |  |  | No |  | Ignore |  |  | Full |  |  | Partial | BP5, BP6, BP7, BP8, BP9, BP10, BP11, BP12, BP13, BP14, BP15, BP16, BP17, BP18. |  | Full |  |  | Full
| RO | SaFIR |  | Outside T2S | Yes |  |  |  | Unknown | Exact testing schedule to be confirmed. |  |  |  |  | SaFIR testing environment is always available for all functionalities. Related to partial release mechanism, testing will be available starting with 1st august 2026. | No |  |  | SaFIR system opens at 7:30 CET (system does not operate overnight) Overnight settlement is subject of ongoing discussions. |  |  |  |  | Yes |  |  |  | Yes | Before 1st testing window |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  |  |  | No |  | Ignore |  |  | Full |  |  | None |  |  | Full |  |  | Full |  |  |  | No |  | Q1 2027.
| SI | KDD |  | In T2S | No |  | No |  | No |  | No |  | Yes | Exact test schedule to be confirmed. |  | No |  | SSS opens at 7:00 am and will remain unchanged. |  | Yes | Already aligned | [5 empty] | Not applicable. | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  | Ignore |  |  | Full |  |  | None |  |  | None |  |  | Full |  |  |  | No |  | To be announced.
| SK | CDCP SR | t+1@cdcp.sk | In T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | Yes |  |  |  | Yes | Already aligned | [5 empty] | Not applicable. | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  | Regarding the partial settlement&release functionality, small exceptions are planned to persist also after T+1 GO LIVE. Regarding the PoA functionality, CDCP SR does and will adhere to it according to the local understanding of the content of the PoA functionality. | Yes | By 2nd testing window |  |  | Regarding the partial settlement and release functionality, small exceptions are planned to persist also after T+1 GO LIVE. Regarding the PoA functionality, CDCP SR does and will adhere to it according to the local understanding of the content of the PoA functionality. | Partial |  | Currently CDCP process only certain types of CA - INTR, REDM for small group of issues. Most of Key Dates are set by issuers. | None |  | No automated BP by Oct 2027. | Partial |  | The market practice in Slovakia is that the market claims are processed between two counterparties of trade in slovak market, without the participation of CSD. Therefore our response to most of the questions in second spreadsheet is Unknown. | Partial |  | CDCP is ready to process transformations even considering that their practice is not common on the slovak market and CDCP has not yet performed these transactions. |  | No |  | Q2 2027. | T+1 handled only in T&Cs.
| NON-EEA COUNTRIES |  |  |  | NON-EEA COUNTRIES | [10 empty] | NON-EEA COUNTRIES | [36 empty] | NON-EEA COUNTRIES | [12 empty] | NON-EEA COUNTRIES
| UK | Euroclear UK & International |  | Outside T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | No |  | EU Specific. |  | No |  | EU Specific. |  | No |  | EU Specific. |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  | Unknown |  |  | Full |  |  | Full |  |  | None |  |  | Full |  |  | There is no change to current UK processes with regards to the implementation of T+1. | Yes |  |  | There is no change to current UK processes with regards to the implementation of T+1.
| CH | SIX-SIS |  | In T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | Yes | Already aligned |  |  | Yes |  |  |  | N/A |  | No non-EUR settlements on T2S. |  | Yes | By 4th testing window |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  |  |  | Yes | By Oct-27 |  |  | PoA Functionality: 'already-matched' is offered to Stock-exchange trades only. | Full |  |  | None |  |  | Partial | Non-applied standards (MC8, MC9, MC18 - MC23), ISO20022 Messages is under analysis. |  | Partial | Non-applied standards (TF6). |  |  | No |  | Unknown. | Market Guides will be updated before Go-Live.
|  |  |  | Outside T2S | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  |  | Yes | Already aligned |  |  | No |  | DVP Cut-off for EUR is 16:15 FOP cut-off is 23:15. |  | No |  | Non-EUR cut-off is 17:00 (or 18:00 for american currencies). |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | Yes | Already available |  |  | No |  |  |  | No |  | Ignore |  | PoA Functionality: 'already-matched' is offered to Stock-exchange trades only. | Full |  |  | None | Following SPTC recommendation. |  | Partial | Non-applied standards (MC8, MC9, MC18 - MC23), ISO20022 Messages is under analysis. |  | Partial | Non-applied standards (TF6).
*Exclusion of Fridays (27 Aug, 03 Sep, 10 Sep)
**Please refer to the next tab for further details on the Corporate Events section

## Corp. Events breakdown
!!! DISCLAIMER !!! |  |  |  | • "HLRM rec." refers to the "High-Level Roadmap" recommendations published by the EU T+1 Industry Committee in June 2025 • "RTS provision" refers to the provisions set out in ESMA's "Final Report On Amendments to the RTS on Settlement Discipline" (October 2025) • "Testing Plan rec." refers to the "Testing Plan" recommendations pubished by the EU T+1 Industry Committee in March 2026 • "AMI-SeCo CEG standards" refers to the standards set out in the "T+1 Coporate Events Harmonised Implementation Guide" published by the AMI-SeCo CEG in March 2026 --> All documents are available on the EU T+1 Industry Committee website under “Guides & Resources”: https://eu-t1.eu/resources-2/ and on ESMA portal: https://www.esma.europa.eu/document/
In case of discrepancies between this table and the latest official communication of the relevant CSD, the latter prevails. ECSDA accepts no liability for the content of this Dashboard, which is provided for the purposes of a high-level overview across European markets and ensuring transparency in advancement of the preparation, allowing CSD participants and other FMIs to prepare the move in an orderly way.
Current dashboard release: June 2026 |  |  |  | Key Dates | [27 empty] | Buyer Protection | [75 empty] | Market Claims | [91 empty] | Transformation
A snapshot will be taken every three/four months and will be made publicly available on the ECSDA website. |  |  |  | CE-01 – Alignment of corporate event key dates with the T+1 standard settlement cycle | [27 empty] | CE-02 – Automation of buyer protection processing | [75 empty] | CE-03 – Automation of market claims processing | [91 empty] | Transformation process
|  |  |  | CSDs to support automatic realignment of CA key dates to T+1 (ex‑date/record‑date same day; reorganisations intervals updated); apply transition rules around go‑live | [27 empty] | Automate end‑to‑end buyer‑protection processing (detect CA, notify chain, capture buyer‑protection/election within shortened windows) | [75 empty] | Implement harmonised ISO messages for claim creation/status/amendments; reduce manual handling in shortened timelines | [91 empty] | Automate transformation of pending transactions (cancel and replace with CA outturn instructions)
|  |  |  | HLRM rec. & AMI-SeCo CEG standards | [27 empty] | HLRM rec. & AMI-SeCo CEG standards | [75 empty] | HLRM rec. & AMI-SeCo CEG standards | [91 empty] | AMI-SeCo CEG standards
| CSD Key Operational Information |  |  | By 11 Oct 2027 | [27 empty] | By 11 Oct 2027 | [75 empty] | By 11 Oct 2027 | [91 empty] | By 11 Oct 2027
|  |  |  | KD1 |  |  |  | KD2 |  |  |  | KD3 |  |  |  | KD4 |  |  |  | KD5 |  |  |  | KD6 |  |  |  | KD7 |  |  |  | BP1 |  |  |  | BP2 |  |  |  | BP3 |  |  |  | BP4 |  |  |  | BP5 |  |  |  | BP6 |  |  |  | BP7 |  |  |  | BP8 |  |  |  | BP9 |  |  |  | BP10 |  |  |  | BP11 |  |  |  | BP12 |  |  |  | BP13 |  |  |  | BP14 |  |  |  | BP15 |  |  |  | BP16 |  |  |  | BP17 |  |  |  | BP18 |  |  |  | BP19 |  |  |  | MC1 |  |  |  | MC2 |  |  |  | MC3 |  |  |  | MC4 |  |  |  | MC5 |  |  |  | MC6 |  |  |  | MC7 |  |  |  | MC8 |  |  |  | MC9 |  |  |  | MC10 |  |  |  | MC11 |  |  |  | MC12 |  |  |  | MC13 |  |  |  | MC14 |  |  |  | MC15 |  |  |  | MC16 |  |  |  | MC17 |  |  |  | MC18 |  |  |  | MC19 |  |  |  | MC20 |  |  |  | MC21 |  |  |  | MC22 |  |  |  | MC23 |  |  |  | TF1 |  |  |  | TF2 |  |  |  | TF3 |  |  |  | TF4 |  |  |  | TF5 |  |  |  | TF6 |  |  |  | TF7 |  |  |  | TF8 |  |  |  | TF9 |  |  |  | TF10 |  |  |  | TF11 |  |  |  | TF12 |  |  |  | TF13 |  |  |  | TF14 |  |  |  | TF15 |  |  |  | TF16
| SSS Jurisdiction | CSD Name | T2S Connectivity | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any) | Will you implement by Oct-27? | If Y, by when? | If N, by when? | Comments (if any)
| EEA COUNTRIES |  |  | EEA COUNTRIES | [27 empty] | EEA COUNTRIES | [75 empty] | EEA COUNTRIES | [91 empty] | EEA COUNTRIES
| AT | OeKB | In T2S | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | Yes | Already implemented |  | Technically already implemented. | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  | No implementation due to legal barrier. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented | [5 empty] | Ongoing analysis of requirement. | Yes | Already implemented |  |  | Unknown |  |  | NTS requirement being analysed with market. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Unknown |  |  | Settlement finality - needs to be analysed. | Unknown |  |  |  | Yes | Already implemented |  |  | Unknown |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented | [5 empty] | Ongoing analysis of requirement. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented | [5 empty] | Ongoing analysis of requirement. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Unknown |  |  | Ongoing analysis of requirement. | Yes | Already implemented |  |  | Yes | Already implemented | [5 empty] | Scenarios 1+2 already implemented/scenario 3 is being analysed. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| BE | Euroclear Bank | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 | [14 empty] | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
|  |  | Outside T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Unknown |  |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Unknown |  |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown
| BE/FR/NL | Euroclear Belgium/France/Netherlands | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 | [14 empty] | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| FI | Euroclear Finland | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  | No automated BP by Oct 2027, no decision on the implementation date. | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | No |  |  | During detection period only at EOD. | Yes | Before 1st testing window |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Before 1st testing window |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  | During detection period only at EOD. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  | No reversal process in the CSD. | No |  |  | ISO market claim messages will not be implemented by Oct 2027, no decision made on the implementation time. | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | No |  |  | During detection period at EOD only. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  | During detection period at EOD only. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| SE | Euroclear Sweden | Outside T2S
| BG | CD AD | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| ES | Iberclear | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| CY | CSE | Outside T2S
| CZ | CDCP CZ | Outside T2S
| DE | Clearstream Europe | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  | 2027-11-01 |  | No |  |  | ISO20022 settlement not available for ICP clients. | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| LU | Clearstream Banking | Outside T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  | 2027-11-01 |  | No |  |  | ISO20022 settlement not available. | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| LU | LuxCSD | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  | 2027-11-01 |  | No |  |  | ISO20022 settlement not available for ICP clients. | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | No |  | 2027-11-01 |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| DK | Euronext Securities ¦ Copenhagen | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
|  |  | Outside T2S (DKK) | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| IT | Euronext Securities ¦ Milan | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Unknown |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| NO | Euronext Securities ¦ Oslo | Outside T2S | Yes | By Oct-27 |  |  | No |  |  |  | Yes | By Oct-27 |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No
| PT | Euronext Securities ¦ Porto | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| GR | Euronext Securities ¦ Athens | Outside T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
| HR | SKDD | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| HU | KELER | In T2S | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown
|  |  | Outside T2S (HUF) | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown
| IS | VBM | Outside T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown
| IS | Nasdaq CSD | Outside T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| LV/EE/LT | Nasdaq CSD | In T2S | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| MT | MSE | In T2S | Yes | By Oct-27 | [6 empty] | Yes | By Oct-27 | [6 empty] | Yes | By Oct-27 |  |  | Yes | By Oct-27 | [6 empty] | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes |  |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Unknown
| PL | KDPW | Outside T2S | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No
| RO | Depozitarul Central | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27
|  |  | Outside T2S (RON) | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  | No NTS for local currency (RON) settlement. | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  | No NTS for local currency (RON) settlement. | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27
| RO | SaFIR | Outside T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 | [6 empty] | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| SI | KDD | In T2S | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | By Oct-27 |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No
| SK | CDCP SR | In T2S | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27 |  |  | Yes | By Oct-27
| NON-EEA COUNTRIES |  |  | NON-EEA COUNTRIES | [27 empty] | NON-EEA COUNTRIES | [75 empty] | NON-EEA COUNTRIES | [91 empty] | NON-EEA COUNTRIES
| UK | Euroclear UK & International | Outside T2S | Yes |  |  |  | Unknown |  |  | Dependent upon UK market & registrars. | Unknown |  |  | Dependent upon UK market & registrars. | Unknown |  |  | Dependent upon UK market & registrars. | Unknown |  |  | Dependent upon UK market & registrars. | Unknown |  |  | Dependent upon UK market. | Unknown |  |  | Dependent upon UK market & registrars. | Yes |  |  |  | Yes |  |  |  | Yes |  |  | Dependent upon UK market. | Yes |  |  | Dependent upon UK market. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  |  | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | Yes |  |  | ISO 20022 currently not available. | No |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | No |  |  | ISO 20022 currently not available. | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | N/A |  |  |  | Yes |  |  |  | N/A |  |  |  | Yes |  |  |  | Yes |  |  |  | Unknown |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | No |  |  | ISO 20022 currently not available. | N/A |  |  | ISO 20022 currently not available. | No |  |  | ISO 20022 currently not available. | No |  |  | ISO 20022 currently not available. | No |  |  | ISO 20022 currently not available. | No |  |  | ISO 20022 currently not available. | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | Yes |  |  | UK relevant times. | Yes |  |  |  | Yes |  |  |  | Yes |  |  |  | N/A |  |  | Not relevant to the UK. | Yes |  |  |  | Yes |  |  |  | Yes
| CH | SIX-SIS | In T2S | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented
|  |  | Outside T2S | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | No |  |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented |  |  | Yes | Already implemented